## Start here
RISK REGISTER TEMPLATE
ZYPHER STRATEGIC SOLUTIONS ¦ zypherstrategicsolutions.com.au ¦ For small businesses and not-for-profits
What this is
A working risk register, not a blank grid. It scores risks on a 5x5 matrix, rates them automatically, tells you when each one is due for review, and summarises the lot on a dashboard that maintains itself.
How to use it
1. Open the 'Risk Register' tab. Row 4 is a filled-in example - overwrite it or delete it. 2. Fill the yellow cells. Grey cells calculate and should not be typed in. 3. Score inherent risk first (before controls), then residual risk (after the controls you actually have). 4. Enter a date in 'Last reviewed'. The next review date sets itself from the risk rating and turns red when overdue. 5. Check the 'Dashboard' tab. It updates on its own.
The three columns people skip
Cause, Existing controls, and Control effectiveness. A register without them records that you are worried; a register with them records what you are actually doing about it. Auditors read those columns first.
Scoring
Likelihood x Consequence, each 1-5. Bands: 1-3 Low, 4-8 Medium, 9-14 High, 15-25 Extreme. Definitions and the full matrix are on the 'Scoring Guide' tab. Change the wording to match your own framework if you have one.
Review cycles
Extreme 30 days, High 90, Medium 180, Low 365 - counted from the date last reviewed. To change the numbers, edit the yellow review-days cells on the Scoring Guide tab.
A note on where this ends
A spreadsheet is the right tool until two people need it at once. At that point it starts drifting - two versions, one person's copy, no history of who changed what. The same register rebuilt in SharePoint and Power Automate keeps the audit trail, chases its own reviews by email, and costs nothing extra if you already pay for Microsoft 365. That is the work Zypher does.
Help with this
Want a second pair of eyes on your register, or help moving it into SharePoint? Book a free 20-minute review: zypherstrategicsolutions.com.au/contact?topic=review ¦ support@zypherstrategicsolutions.com.au
Using this template
Free to use inside your own organisation. The Zypher name and notices on every tab are part of the template and are locked - please leave them in place, and do not resell or redistribute the file. Send people to zypherstrategicsolutions.com.au/resources instead. The sheets are protected only so that the formulas and notices stay intact; the yellow cells are yours to edit.
Provided as a general template. It is not legal, clinical or financial advice, and it does not by itself satisfy any particular regulatory obligation - check it against the standards that apply to your organisation.
© 2026 Zypher Strategic Solutions (ABN 11 992 914 188). Free to use inside your own organisation. The Zypher name and notices must stay in place; do not resell or redistribute this file - point people to zypherstrategicsolutions.com.au/resources instead.

## Risk Register
RISK REGISTER
ZYPHER STRATEGIC SOLUTIONS ¦ zypherstrategicsolutions.com.au ¦ Yellow = fill in · Grey = calculates itself · Scoring definitions: see Scoring Guide tab
Risk ID | Date identified | Category | Risk description (what could happen) | Cause (why it could happen) | Potential consequence | Inherent likelihood (1-5) | Inherent consequence (1-5) | Inherent score | Inherent rating | Existing controls | Control effectiveness | Residual likelihood (1-5) | Residual consequence (1-5) | Residual score | Residual rating | Risk owner | Treatment / further action | Target date | Status | Last reviewed | Next review due
R001 | 2026-10-02 | Work Health & Safety | Volunteer driver injured during a home delivery run | Uneven paths and unlit entryways at client homes; no formal pre-delivery hazard check | Lost-time injury, workers compensation claim, loss of volunteer capacity on that run | 3 | 4 | 12 | High | Volunteer induction covers manual handling; incident reporting form in use; annual driver briefing | Partially effective | 2 | 4 | 8 | Medium | Operations Manager | Add a 2-minute site hazard check to the delivery app; escalate repeat hazard sites to the client's family | 2026-12-19 | In treatment | 2026-10-02 | 2027-03-31
© 2026 Zypher Strategic Solutions (ABN 11 992 914 188). Free to use inside your own organisation. The Zypher name and notices must stay in place; do not resell or redistribute this file - point people to zypherstrategicsolutions.com.au/resources instead.
Formulas:
Next review due = IF(OR([Last reviewed]="",[Residual rating]=""),"",[Last reviewed]+INDEX('Scoring Guide'!$H13:H16,MATCH([Residual rating],'Scoring Guide'!$E13:E16,0)))
Note on I3: Likelihood x Consequence. Calculates automatically.
Note on V3: Calculates from Last reviewed + the review cycle for the residual rating. Cycles are set on the Scoring Guide tab (default Extreme 30 days, High 90, Medium 180, Low 365). Turns red once overdue.

## Scoring Guide
SCORING GUIDE
ZYPHER STRATEGIC SOLUTIONS ¦ zypherstrategicsolutions.com.au
Likelihood |  |  | Risk matrix (Likelihood x Consequence)
Score | Rating | Description
5 | Almost certain | Expected to occur in most circumstances — more than once a year | L \ C | 1 | 2 | 3 | 4 | 5
4 | Likely | Will probably occur — about once a year | 5 | 5 | 10 | 15 | 20 | 25
3 | Possible | Might occur at some time — once every 1-3 years | 4 | 4 | 8 | 12 | 16 | 20
2 | Unlikely | Could occur but not expected — once every 3-10 years | 3 | 3 | 6 | 9 | 12 | 15
1 | Rare | Only in exceptional circumstances — less than once in 10 years | 2 | 2 | 4 | 6 | 8 | 10
|  |  | 1 | 1 | 2 | 3 | 4 | 5
Consequence
Score | Rating | Description | 5 4 3 2 1: Bands; 15 12 9 6 3: Review (days)
5 | Severe | Death or permanent disability; loss of funding or licence; sustained national coverage | 5 4 3 2 1: Low; 5 4 3 2 1: 1 - 3; 15 12 9 6 3: 365
4 | Major | Serious injury needing hospitalisation; regulatory sanction; major service disruption | 5 4 3 2 1: Medium; 5 4 3 2 1: 4 - 8; 15 12 9 6 3: 180
3 | Moderate | Injury needing medical treatment; reportable breach; service disrupted for days | 5 4 3 2 1: High; 5 4 3 2 1: 9 - 14; 15 12 9 6 3: 90
2 | Minor | First aid injury; minor non-compliance resolved internally; brief disruption | 5 4 3 2 1: Extreme; 5 4 3 2 1: 15 - 25; 15 12 9 6 3: 30
1 | Insignificant | No injury; no compliance impact; absorbed in normal operations
The yellow cells are editable: change the descriptions to match your own framework, and the review days (default Extreme 30, High 90, Medium 180, Low 365, counted from the date last reviewed). The register's Next review due column follows these numbers.
© 2026 Zypher Strategic Solutions (ABN 11 992 914 188). Free to use inside your own organisation. The Zypher name and notices must stay in place; do not resell or redistribute this file - point people to zypherstrategicsolutions.com.au/resources instead.

## Dashboard
RISK DASHBOARD
ZYPHER STRATEGIC SOLUTIONS ¦ zypherstrategicsolutions.com.au ¦ Updates itself
Residual risk profile |  | By status |  | Attention
Rating | Count | Status | Count | Measure | Count
Extreme | 0 | Open | 0 | Reviews overdue | 0
High | 0 | In treatment | 1 | Extreme or High open | 0
Medium | 1 | Monitoring | 0 | No owner assigned | 0
Low | 0 | Closed | 0 | No treatment recorded | 0
Total risks recorded | 1
By category
Category | Count
Governance | 0
Financial | 0
Operational | 0
Work Health & Safety | 1
Clinical / Care | 0
Compliance & Regulatory | 0
People & Culture | 0
Information & Cyber | 0
Reputation | 0
Service Continuity | 0
Supplier / Contract | 0
Privacy & Records | 0
© 2026 Zypher Strategic Solutions (ABN 11 992 914 188). Free to use inside your own organisation. The Zypher name and notices must stay in place; do not resell or redistribute this file - point people to zypherstrategicsolutions.com.au/resources instead.

## Lists (hidden)
Category | Scale | ControlEffectiveness | Status | Rating
Governance | 1 | Effective | Open | Low
Financial | 2 | Partially effective | In treatment | Medium
Operational | 3 | Ineffective | Monitoring | High
Work Health & Safety | 4 | Not yet assessed | Closed | Extreme
Clinical / Care | 5
Compliance & Regulatory
People & Culture
Information & Cyber
Reputation
Service Continuity
Supplier / Contract
Privacy & Records